## Sheet1
Current State | Sequence | Number Of Failures | Issues | SWQA | Activly work | Priority | Estimate of time to complete (Are the time to edit does not include time to test or retest or re-edit)
PASS | Debug Test |  |  | TB |  | Lowest | DONE
PASS | Call Courtesy HE |  |  | TB |  | Highest | DONE
PASS | Bootloader |  |  | TB |  | Low | DONE
PASS | Currently working on Display and interactions |  |  | TB |  | Low | DONE | Highest
PASS | UI |  |  | TB |  | Low | DONE | High
PASS | Display |  |  | TB |  | Low | DONE | Low
PASS | Lid Interactions |  |  | TB |  | Low | DONE | Lowest
PASS | Cycle Knob Interactions |  |  | TB |  | Low | DONE
PASS | Idle State: Key Press, Loads, Lid Interaction |  |  | TB |  | Low | DONE
PASS | Estimated Cycle Time in Fixed Level Fill |  |  | TB |  | Low | DONE | DONE
PASS | Estimated Cycle Time in Volume Fill |  |  | TB |  | Low | DONE
PASS | Common 2015_QA Tests |  |  | TB |  | Highest | DONE
PASS | 2015_QA: Cycle 83 - Adaptive Agitate Manual Load Size (LE) |  |  | TB |  | Low | DONE
PASS | Lid and Fill Interactions |  |  | TB |  | Low | DONE
PASS | Service Mode |  |  | TB |  | Highest | DONE
SLB Only Testing
have not run | Personality Knob Mapping |  |  |  |  | Lowest | Need to rewrite, unknown
have not run | ADC knobs |  |  |  |  | High | 4 hours
have not run | Service Mode | Not implemented |  |  |  | Highest | A Day
Washer
have not run | Fault Code Tests |  |  |  |  | Highest | Few Days to a week
have not run | Consumer Error Mode LE |  |  | Just worked with out edit |  | Lowest | Few hours
PASS | Resource Watchdogs Test |  |  | TB |  | Lowest | Few Hours
PASS | OOB Notifications for WashRinse Cycles |  |  | TB |  | Highest | DONE
PASS | OOB Redistribution Test |  |  | TB |  | Highest | DONE
PASS | OOB Parametric Accel Test |  |  | TB |  | Highest | DONE
PASS | OOB Parametric Steady State Test |  |  | TB |  | Highest | DONE
PASS | Allowables by Cycle Test |  |  | TB |  | Low | DONE
PASS | Defaults by Cycle Test |  |  | TB |  | Low | DONE
PASS | Parametric UI Tests |  |  | TB |  | Low | DONE
FAIL | Load Size Unknown Fill Test | Firmware issue Not going to run on Cetauro |  | TB |  | Low | 1 Hour
PASS | Flood Warning Parametric Test |  |  | TB |  | High | DONE
PASS | Wet Load Sense Parametric Test |  |  | TB |  | Low | DONE
PASS | Dry Load Sense Parametric Test |  |  | TB |  | Low | DONE
have not run | Cycle History |  |  |  |  | Low | Few Days to a week
have not run | Service Compliance UI | Firware Issue |  | TB |  | Highest | Few hours
PASS | Service Compliance MC |  |  | TB |  | Highest | DONE
have not run | Service Diagnostics ERDs |  |  |  |  | Highest | 1 Hour
have not run | Motor Profiles |  |  |  |  | Highest | Few hours
have not run | Fault Code Tests |  |  |  |  | Highest | Few Days to a week
PASS | Child Safety Algorithm |  |  | TB |  | Highest | DONE
PASS | ATC Algorithm |  |  | TB | Currenlty working | High | A Day
PASS | Version Command |  |  | TB |  | Lowest | DONE
FAIL | Test Mode |  |  | TB | Currenlty working | Lowest | 1 Hour
PASS | Water Valve Flow Rate |  |  | TB |  | High | DONE
PASS | Accumulated Tub Gallon |  |  | TB |  | High | DONE
PASS | ERD Subscription |  |  | TB |  | Low | DONE
PASS | Drive Profile Selection |  |  | TB |  | High | DONE
FAIL | Common Code ERD Tests |  |  | TB | Currenlty working | Highest | Few Days
PASS | Reset Gallons Tests |  |  | TB |  | Low | DONE
PASS | Update Tub Volume (#59) |  |  | TB |  | Low | DONE
FAIL | Continuous Cycle Mode |  |  | TB | Currenlty working | Low | Few hours
PASS | Gear Ratio Verification Test |  |  | TB |  | Low | DONE
PASS | System Runtime |  |  | TB |  | Low | DONE
PASS | Backsplash Configuration ERD |  |  | TB |  | Low | DONE
PASS | NV Restricted ERDs |  |  | TB |  | Low | DONE
| SLB Only Testing |  |  | CS
PASS | Wet Load Sense Algorithm |  |  | CS |  | Low | DONE
FAIL | Redundant Micro |  |  | CS |  | High | 1 Hour
FAIL | Thermistor Micro |  |  | CS |  | High | 1 Hour
PASS | Pressure Sensor Calibration |  |  | CS |  | High | DONE
PASS | Cycle Preprocessor |  |  | CS |  | Low | DONE
FAIL | Lid Enforcer |  |  | CS |  | Low | 1 Hour
PASS | Exit Low Power Mode SLB |  |  | CS |  | Low | DONE
PASS | Arc Sensor Test |  |  | CS |  | High | DONE
FAIL | Hall Sensor Test |  |  | CS |  | High | 1 Hour
FAIL | Pressure Sensor Test |  |  | CS |  | High | 1 Hour
PASS | Current Sensor Test |  |  | CS |  | High | DONE
FAIL | Thermistor Test |  |  | CS |  | High | 1 Hour
PASS | Voltage Sensor Test |  |  | CS |  | High | DONE
PASS | Open Lid |  |  | CS |  | Low | DONE
PASS | Wait for lid open | [5 empty] | DONE
PASS | Close Lid | [5 empty] | DONE
PASS | Wait for lid closed | [5 empty] | DONE
PASS | Stack Usage | [5 empty] | DONE
PASS | Read Stack - SLB | [5 empty] | DONE
PASS | Stack Usage Test - SLB | [5 empty] | DONE
PASS | Dry Load Sense Profile |  |  | Just worked with out edit |  | High | Few hours
PASS | Motor To Idle on Stop and Pause |  |  | TB |  | High | Few hours
PASS | Mode Shift |  |  | TB |  | High | Few hours
PASS | PI Gains |  |  | TB |  | Low | Few hours
have not run | Brass Matrix |  |  | DD |  | Low | Few hours
PASS | Current Sensor test |  |  | TB |  | Low | Few hours
PASS | Lid Unlock Management During Spin |  |  | TB |  | High | 1 Hour
PASS | Lid Lock Management During Spin |  |  | TB |  | High | 1 Hour
PASS | Adaptive Drain |  |  | TB |  | High | 1 Hour
PASS | Water Valve Enable Relay |  |  | Just worked with out edit |  | Low | 1 Hour